## Sheet1
Development Process
Agile approach
Weekly Sprints
Milestones ~2 weeks
Weekly Status Reports
Development Plan
First Trimester | [9 empty] | Second Trimester | [9 empty] | Third Trimester
Finish all planning and system requirements documents then begin prototyping | [9 empty] | Have the prototyping done by week 2 and begin final development. Begin integration testing | [9 empty] | Finish integration testing by week 2 and finalize the project. Build the project presentation
Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10
Initial meeting. Set the team and the project | Have the proposal done - project decided | Identify and order prototyping devices |  | Technology and Concept Investigation report done Date: 10/3/18 |  | Finish system repuirements and interface design Date: 10/19/18 | Begin Prototyping Hardware. System requirements specification done |  | Complete cycle report Date: 11/9/18 |  | Finish Prototyping Date: 12/7/18 | [5 empty] | Design Deliverables Done 2/1/19 |  |  |  | Finish integration testing Date: 3/15/19 |  |  |  |  | Final Presentation Prepared Date: 4/26/18
Finish all planning and system requirements documents then begin prototyping Week 2: Tech and concept investigation; Finish all planning and system requirements documents then begin prototyping Week 6: System Requirments Interface Design; Finish all planning and system requirements documents then begin prototyping Week 8: Prototyping (~7 weeks) Design Planning |  |  | Design Work Iterative Testing | [5 empty] | System and Integration Testing |  |  |  | Work on Final Presentation Finalize all doucmentation Finalize product presentation |  |  |  | Practive Final Prenstation Make Final revisions to documents